ADAMS INFINITE LEGACY

A California Nonprofit Public Benefit Corporation

FOUNDATION LAUNCH CHECKLIST

In the order to do them

A step-by-step guide to launching the foundation, arranged in the sequence to actually follow. Work top to bottom — later steps depend on earlier ones. Steps shown in red are time-sensitive. Check items off in the portal as you complete them.

Stage 1 · Form the Corporation & Get Your Tax ID

☐  1.  File Articles of Incorporation with the CA Secretary of State

Go to the California Secretary of State's website (bizfileOnline) and file the Articles of Incorporation for a 501(c)(3). Once approved you get a stamped copy — save it; it's the foundation's birth certificate.

☐  2.  Obtain a federal Employer Identification Number (IRS Form SS-4)

Apply for a free EIN (the foundation's tax ID) at IRS.gov — search ‘apply for EIN online.’ Takes about 10 minutes and you get the number right away. You'll need it for the bank account and the 501(c)(3) application.

Stage 2 · Hold the Organizational Board Meeting

Everything in this stage is decided and recorded at your first official board meeting.

☐  3.  Hold the organizational meeting of the Board of Directors

Gather all seven directors (in person or by video) for the first official meeting. Use the Organizational Board Minutes as your agenda and record what's decided.

☐  4.  Adopt & certify the Bylaws

Have your attorney review the Bylaws, then the board votes to adopt them at the meeting. Sign them in the portal and keep a copy in your records.

☐  5.  Elect officers and record them in the minutes

At the meeting, formally confirm who holds each officer role (President, Treasurer, Secretary, etc.) and write it into the minutes.

☐  6.  Set the corporation's principal office address

Decide the official mailing address for the foundation and record it in the Bylaws and minutes. It can be your home or a P.O. box.

☐  7.  Establish the fiscal year-end (December 31)

Confirm the foundation's financial year runs January 1–December 31 (the standard choice). This sets when your taxes and reports are due.

☐  8.  Confirm directors serve without compensation (expenses only)

Confirm in the minutes that directors volunteer their time and are only paid back for real expenses (like travel) — never a salary.

☐  9.  Adopt the Conflict of Interest Policy & collect signed disclosures

Adopt the Conflict of Interest Policy at the board meeting, then have every director sign the disclosure form. Keep the signed forms on file.

☐  10.  Adopt the Document Retention & Destruction Policy

Adopt the policy that says which records to keep, for how long, and when it's safe to destroy old ones.

☐  11.  Adopt the Whistleblower Policy

Adopt the policy that lets staff or volunteers report concerns without fear of retaliation.

☐  12.  Adopt the Gift Acceptance Policy

Adopt the policy setting rules for what kinds of donations you'll accept (cash easily; certain property only with conditions).

☐  13.  Adopt the Privacy Notice & Data Protection Policy

Adopt the policy explaining how you protect donors' and recipients' personal information.

☐  14.  Adopt the Financial Assistance Eligibility & Selection Criteria

Write down who qualifies for help and how you'll choose recipients (illness type, need, documents required, award amounts). The board approves it.

☐  15.  Approve & plan the “Get Well Soon” Wellness Festival

Set a date, budget, and plan for the Get Well Soon Wellness Festival, and have the board approve it as an official program of the foundation.

☐  16.  Ratify prior organizational acts of the directors & officers

In the minutes, add a line approving any actions taken before the meeting (like reserving the name or early expenses) so they become official.

☐  17.  Approve & sign the Organizational Board Minutes

After the meeting, finish the Minutes with the real dates and decisions. The Secretary and President sign them here in the portal, then file them with your records.

Stage 3 · Banking, Signatories & Insurance

☐  18.  Open the corporate bank account & designate authorized signatories

Take your stamped Articles, EIN letter, and signed Board Resolution to a bank and open the foundation's account. Name who's allowed to sign. (This is why the EIN and signed minutes come first.)

☐  19.  Set the two-signature threshold for large disbursements

Decide the dollar amount above which two people must approve a payment (many small nonprofits use $2,500) and record it in the minutes.

☐  20.  Obtain D&O and general liability insurance

Get quotes for Directors & Officers (D&O) insurance and general liability insurance, then buy coverage to protect the board and the organization.

Stage 4 · Tax Exemption & Charitable Registration

These have real deadlines — watch the dates in red.

☐  21.  File the Statement of Information (Form SI-100)

File Form SI-100 with the CA Secretary of State (online, small fee). It lists your officers and address, and you re-file it every two years.

Deadline: within 90 days of filing the Articles.

☐  22.  File IRS Form 1023 / 1023-EZ for 501(c)(3) recognition & pay the user fee

File IRS Form 1023 (or the shorter 1023-EZ if you qualify) to become an official 501(c)(3). There's a fee (about $275–$600). This is the big one — consider having your accountant help.

Best practice: file within 27 months of the Articles so your exemption is retroactive to formation.

☐  23.  Register with the CA Attorney General Registry of Charities (Form CT-1)

Register with the California Attorney General's Registry of Charities (Form CT-1) so you can legally fundraise.

Deadline: within 30 days of receiving any money or assets — and before you fundraise.

☐  24.  File CA FTB Form 3500A

File California Form 3500A so the foundation is also exempt from state income tax.

Do this after the IRS determination letter arrives — it depends on federal approval.

☐  25.  Calendar annual renewals (Form RRF-1) & Form 990 filings

Put the yearly deadlines on your calendar: the California renewal (Form RRF-1) and the IRS Form 990. Missing these can cost your tax-exempt status.

Stage 5 · Ready to Raise Money

☐  26.  Set sponsorship tier prices in the Prospectus

Decide the price for each sponsor level (Presenting, Gold, Silver, Community) in the Prospectus — then it's ready to send to potential sponsors.

☐  27.  Finalize the donor acknowledgment letter templates

Review the four donor thank-you letter templates and add your EIN so they're ready to send the moment someone donates.

Tip: Work top to bottom — each step builds on the ones before it. Your EIN, bank account, and 501(c)(3) status unlock everything else, so formation and tax steps come first. A few items (insurance, the program and fundraising materials) can be prepared in parallel once the board has met. Loop in your attorney or accountant on the legal and financial steps — especially the Bylaws, the Form 1023, and the assistance criteria.